## Slide 1: Recruitment Progress
2nd April 2015

## Slide 2
National Paramedics
All national paramedics for 14/15 have now joined the service. The final figure reduced from 10 to 7
We have recently conducted an assessment centre in Ireland for qualified Paramedics and have made 9 offers; 4 candidates have confirmed their ability to start with LAS in April. The remaining 5 are anticipated to start training in either May or June; these will not be reflected in our figures until they have confirmed their start dates.
TEACs
All 77 TEACs (trainee emergency ambulance crew) are currently in training and will join the service between January and March 2015
15 of the 77 TEACs joined operations on 19th January 2015
11 of the 77 TEACs went into supervision on Monday 9th February
20 of the 77 TEACs went into supervision on Monday 2nd March
8 of the 77 TEACs went into supervision on Monday 9th March
The remaining 23 went into supervision on Monday 23rd March
The current TEAC recruitment drive has resulted in;
  63 offers accepted and candidates booked on to courses
  We have a further 94 candidates who have accepted offers and we are negotiating their start dates subject to C1 driving and references
  102 interviews are in the process of being booked
  89 awaiting assessment are booked (if successful these candidates will then be interviewed)
  136 applications are being screened
International Paramedics
We have now completed our 15/16 international recruitment drive and we have made a total of 225 offers of employment
All 97 international candidates for 14/15 Q4 have now started:
  10 started training on 5th January
  32 started training on the 26 January
  19 started training on the 9th February
  36 started training on the 2nd March
We are continuing to work with the HCPC, to discuss outstanding registrations, and resolve issues encountered with registration process
Recruitment Summary

## Slide 3
Chart: 
| January | February | March
EAC planned | 24 | 12 | 75
EAC actual | 15 | 11 | 52
National Paramedics planned | 3 | 0 | 0
National Paramedics actual | 5 | 0 | 8
International Paramedics planned | 63 | 8 | 23
International Paramedics actual | 42 | 19 | 37
Column1
Column2
Summary
186 staff joined our service in Q4 and have illustrated the final position for these starters below. The total international candidates wishing to start in Q4 has reduced from 105 to 97 against a target of 94 wte.
Recruitment performance against plan: 14/15 Q4
WTES
January plan: 90 wte
January actual: 62 wte
Difference: planning assumption on international paramedics through incentivisation; some EACs not completing training, national paramedics wishing to start training in March
February plan: 20 wte
February actual: 30 wte
Difference: planning assumption on international paramedics through incentivisation; 1 EAC not completing training, internationals withdrawing and deferring
March plan: 93 wte
March actual: 94 wte
Difference: planning assumption on international paramedics through incentivisation; some EACs not completing training, national paramedics wishing to start training in March
Candidates have started
All candidates have started
19 started
30
42
51 started
7
11 started
36 started
7 started

## Slide 4
4
Chart: 
| April | May | June
EAC planned | 0 | 36 | 53
EAC actual | 0 | 96 | 30
National Paramedics planned | 0 | 0 | 0
National Paramedics actual | 0 | 0 | 0
International Paramedics planned | 12 | 10 | 5
International Paramedics actual | 10 | 20 | 7
#REF!
Summary
We are currently expecting 163 starters against a plan 119 staff to join our service in Q1 and have illustrated below our confidence levels for these starters. The international starters continue to fluctuate between months.
Recruitment performance against plan: 15/16 Q1
WTES
April plan: 12 wte
April actual:10 wte
Difference: Internationals changing start dates
May plan: 46 wte
May actual: 116 wte
Difference: TEACs completing training
June plan: 58 wte
June actual: 37 wte
Difference: Internationals changing start dates
20
Confidence level
82
7
Confidence level
18
Confidence level
4

## Slide 5
2014/15 Forecast Outturn
The table below details our forecast outturn for 14/15. This is based on the month 11 position , anticipated turnover and forecasted starters for Feb -March. This position is improved from forecast.
2014-15 Establishment | 2014/15 establishment | In post (M11) | Vacancies | Expected turnover ( M12) - 5 paramedics and 2 non paramedics pw | Anticipated new starters 14/15 March | Total in post staff at year end | Vacancies remaining going into 15/16
Paramedics | 1,774.80 | 1434.34 | 340.46 | 20 | 36 | 1450.34 | 324.46
Non Paramedics | 1,281.72 | 1246.61 | 35.11 | 8 | 15 | 1253.61 | 28.11
Total | 3,056.52 | 2,680.95 | 375.57 | 28 | 51 | 2703.95 | 352.57

## Slide 6
Chart: 
| October | November | December | January | February | March
starters | 50.5 | 29 | 0 | 62 | 30 | 95
Leavers | 27 | 17 | 13 | 30 | 27 | 30
net
cumulative | 23.5 | 35.5 | 22.5 | 54.5 | 57.5 | 122.5
WTES
Based on actuals
Based on actual leaver and starters data (Oct-Feb), planned interview schedule, confirmed starters in training and predicted leavers we are anticipating a significant shift in the in-post frontline staffing levels in March. The projected leavers rate does not reflect any measures to reduce attrition.
Starters and Leavers
From October to March 265 new frontline staff have joined LAS compared to 144 leavers