## ACTION LOG
Equality Committee - 8 May 2018
Ref. | Action | Owner | Date raised | Date due | STATUS | Date completed | Comments / updates (i.e. why action is not resolved / completed)
On track
1 month late
Over 1 month late
CLOSED
EDC18/05 | CR to provide further breakdown (Gender Pay Report) | CR | 2018-05-08 | 2018-07-23 | On track
EDC18/05 | CR to provide further Gender Pay Report for December Committee | CR | 2018-05-08 | 2018-12-01 | On track
EDC18/07 | MB to send the Workfoce Disability Standards metrix once agreed to Committee members | MB | 2018-05-08 | tbc | On track
EDC18/07 | ML to send 'Beans' disability awareness video to MB and KM | ML | 2018-05-08 | 2018-05-31 | CLOSED
EDC18/08 | The revised Equality Impact Assessment would be published to the Pulse | MB | 2018-05-08 | 2018-05-31 | On track
EDC18/08 | SB and MB to ensure that information about Ramadan would be made available on the Pulse | SB/MB | 2018-05-08 | 2018-05-10 | CLOSED
EDC18/08 | Update on the use of Exit Interviews | MB | 2018-05-08 | 2018-07-23 | On track

## Do not delete (hidden)
On track | Range = RAG
1 month late
Over 1 month late
CLOSED
Yes | Range = Attended
No